## Sheet1
Task No. | Module | Task Name | Assignee | Status | Deadline | Comments
1 | Login & user registration | Break entire function into minor tasks and create service backlog | Tirone | In-Progress | 7th May 2021
2 | User registration | User : Create model class with validations | Tirone | Complete | 5th May 2021
3 | User registration | User: Connect to db | Tirone | Complete | 5th May 2021
4 | User registration | User: Creation service | Tirone | Complete | 5th May 2021
5 | User registration | User: Testing the creation service | Tirone | Complete | 5th May 2021
6 | Item | Break entire function into minor tasks and create service backlog | Savvy | Complete | 5th May 2021
7 | Item | Item: Create model class | Savvy | Complete | 5th May 2021
8 | Item | Item: Connect to db | Savvy | Complete | 5th May 2021
9 | Item | Item: Creation service | Savvy | Complete | 5th May 2021
10 | Item | Item: Testing the item creation service | Savvy | Complete | 5th May 2021
11 | Item | Item: Delete Service and Testing | Savvy | Complete | 5th May 2021
12 | Shopping cart | Item view, shopping cart : Break entire function into minor tasks and create service backlog | Wishva | In-Progress | 7th May 2021
13 | Login page | Designing login page - Validations, Popups | Wishva | In-Progress | 7th May 2021
14 | Dummy | Dummy services - Break entire function into minor tasks and create service backlog | Himantha | In-Progress | 5th May 2021
15 | Design Registration page | Designing registration page - Validations, Popups | Wishva | In-Progress | 7th May 2021
16 | Report | Start working on high level diagram for the report | Himantha | In-Progress | 7th May 2021
18 | Item | Item: Update Service creation | Savvy | In-Progress | 7th May 2021
19 | Item | Item: Update Service testing | Savvy | In-Progress | 7th May 2021
20 | Login | Login Service | Tirone | In-Progress | 7th May 2021
21
22
23
Crown Shopping
Landing page
| Savvy | Conference details Add/Edit | Charitha
Template download
| Himantha | Registration & Uploading documents - Atendee *,Researcher and Workshop conductor | Sandunika
Display page - Reviewing page and Display approved page
| Wishva | Approval and rejection | Gale
Notification Manager
| Tirone | Payment page | Nime
Login function